## Sheet1
IDP Pipeline Build |  |  | IDP DataOps Cosnole Build |  |  | Onboarding Fed Teams to IDP
Pipeline Activity | Team | ETA | Capability/Feature | Team | ETA | Before DataOps Console (Manual)
File Source Activity | IDP (Wipro) |  | Data Model (metadata, inventory, tracking) | Core |  | Activities/Task | Team | SLA
Snowflake Source Activity | IDP (Wipro) |  | Client, Account Partner management | IDP (Optum) |  | Workspace Provisioning | IDP
Cosmos Source Activity | IDP (Wipro) |  | Import Pipelines from Template | IDP (Optum) |  | Deploy Metadata Model | IDP
Mongo Source Activity | IDP (Wipro) |  | Deploy Pipelines as Job | IDP (Optum) |  | Pipeline Import | IDP
RDBMS Source Activity | IDP (Wipro) |  | Job Run and History | IDP (Optum) |  | Snowflake Tables | Fed Team
Kafka Source Activity | IDP (Wipro) |  | Reports (Lineage, Quality, Recon) | IDP (Optum) |  | Inbound Storage Account | IDP
API Source Activity | IDP (Wipro) |  | Data Catalog | IDP (Optum) |  | Setup Clients, Accounts, Parameters | Fed Team
|  |  | Market Place | IDP (Optum) |  | Deploy Airflow Jobs | IDP + Fed Team
Validate Activity | IDP (Wipro) |  |  |  |  | Test Airflow Jobs | Fed Team
Pre Transform Activity | IDP (Wipro) |  |  |  |  | Promote to other environments | IPD+ Fed Team
Canonical Transform Activity | IDP (Wipro)
FHIR Transform Activity | ECDH
Post Transform Activity | IDP (Wipro)
Async Activity (Send it Kafka) | IDP (Wipro)
Enrichment Activity | IDP (Wipro) |  |  |  |  | After DataOps Console (Self Service)
[6 empty] | Workspace Provisioning | IDP
File Sink Activity | IDP (Wipro) |  |  |  |  | Deploy Metadata Model | IDP
Snowflake Sink Activity | IDP (Wipro) |  |  |  |  | Pipeline Import | Fed Team
Cosmos Sink Activity | IDP (Wipro) |  |  |  |  | Snowflake Tables | Fed Team
Mongo Sink Activity | ECDH |  |  |  |  | Inbound Storage Account | Fed Team
RDBMS Sink Activity | IDP (Wipro) |  |  |  |  | Setup Clients, Accounts, Parameters | Fed Team
API Sink Activity | IDP (Wipro) |  |  |  |  | Deploy Airflow Jobs | Fed Team
Kafka Sink Actcivity | IDP (Wipro) |  |  |  |  | Test Airflow Jobs | Fed Team
[6 empty] | Promote to other environments | Fed Team
Pipeline Template Creation (128 Templates) | IDP (Wipro)
Airflow DAGs | IDP (Wipro)
Retry Pipeline for for each activity for Pipelines | IDP (Wipro)
Clean Up Pipeline | IDP (Wipro)
High - Required for all
Required by ECDH
Only EEDM needed
CDP, Rosters & all silver layer and gold layer required